SHOPWAVE

Professional E-Commerce MVP

Agile Project Documentation  ·  Scrum Framework

| Document Type | Project Charter + Product Backlog + Sprint Plans |
| --- | --- |
| Methodology | Scrum / Agile (2-Week Sprints) |
| Tech Stack | Angular · Node.js + Express · MongoDB |
| Total Story Points | ~191 points across 39 User Stories |

# SECTION 1 — PROJECT CHARTER

## 1.1  Project Overview

| Project Name | ShopWave — Professional E-Commerce MVP |
| --- | --- |
| Version | 1.0 |
| Date | March 26, 2026 |
| Document Owner | Team Lead / Full-Stack Developer |
| Methodology | Scrum / Agile (2-week Sprints) |
| Tech Stack | Angular · Node.js + Express · MongoDB · JWT · Stripe / Paymob |

## 1.2  Vision Statement

"To deliver a scalable, secure, and intuitive e-commerce platform that enables businesses to sell online effectively — built with best-practice Agile engineering and modern web technologies."

## 1.3  Objectives

- Technical: Implement a production-grade REST API with JWT authentication, role-based access control, and full CRUD operations.

- Functional: Deliver a complete customer buying journey — browse → cart → checkout → payment — integrated with a real payment gateway.

- Quality: Achieve ≥ 60% unit test coverage; zero critical security vulnerabilities; full API documentation via Swagger.

- Agile: Follow the Scrum framework with documented sprints, a groomed backlog, velocity tracking, and retrospectives.

- Academic: Produce a graduation-level deliverable demonstrating mastery of Angular, Node.js, MongoDB, and Agile practices.

## 1.4  Stakeholders

| Stakeholder | Type | Role / Interest | Influence |
| --- | --- | --- | --- |
| Product Owner / Supervisor | Academic | Approves scope & deliverables | High |
| Team Lead (Full-Stack Dev) | Internal | Architecture, code, delivery | High |
| Frontend Developer(s) | Internal | Angular UI implementation | High |
| Backend Developer(s) | Internal | API & database implementation | High |
| End Customers | External | Browse, search & purchase products | High |
| Admin Users | External | Manage products, orders & users | Medium |
| Payment Gateway (Stripe/Paymob) | Third-Party | Process transactions securely | Medium |

## 1.5  Assumptions & Constraints

### Assumptions

- Team has working knowledge of Angular, Node.js, and MongoDB.

- Payment gateway will be used in sandbox/test mode only.

- Cloud storage (Cloudinary) will handle product image uploads.

- A free-tier MongoDB Atlas cluster is sufficient for development.

### Constraints

- Academic deadline defines the final release date (Sprint 6).

- Team size: 2–4 developers; no dedicated QA or DevOps resource.

- Budget: zero — all tools and services must use free tiers.

## 1.6  Success Criteria

| ID | Category | Acceptance Criterion |
| --- | --- | --- |
| SC-01 | Authentication | JWT login/register with role-based access (Admin & Customer) fully functional |
| SC-02 | Product Catalog | Admin can CRUD products; customers can browse, filter, and search |
| SC-03 | Shopping Cart | Add/remove/update cart items with real-time totals |
| SC-04 | Checkout & Payment | End-to-end checkout integrated with Stripe or Paymob (test mode) |
| SC-05 | Order Management | Customers can view order history; Admins can update order status |
| SC-06 | Performance | API response time < 500ms for 95% of requests under normal load |
| SC-07 | Security | No critical OWASP Top 10 vulnerabilities; all endpoints authenticated |
| SC-08 | Code Quality | Unit test coverage ≥ 60%; CI pipeline passes on every merge |
| SC-09 | Documentation | Swagger/OpenAPI docs for all API endpoints; README up to date |
| SC-10 | Deployment | App deployed to a cloud environment (Vercel / Railway / Render) |

# SECTION 2 — PRODUCT BACKLOG

## 2.1  Epics

- EPIC-01 Authentication & User Management: Registration, login, JWT, OAuth, profile.

- EPIC-02 Product Catalog: CRUD, search, filter, pagination, product detail.

- EPIC-03 Shopping Cart: Add/update/remove items, persist cart, totals.

- EPIC-04 Checkout & Payment: Shipping, payment gateway, confirmation email.

- EPIC-05 Order Management: Order history, status tracking, cancellation.

- EPIC-06 Admin Dashboard: KPI overview, user management, reports.

- EPIC-07 Reviews & Ratings: Customer reviews, moderation.

- EPIC-08 Notifications: Email alerts for order status and low stock.

## 2.2  User Story Format

Format: "As a [User Role], I want to [Action/Goal], so that [Business Value]."

Story Points: Fibonacci scale — 1 | 2 | 3 | 5 | 8 | 13 | 21

## 2.3  Full Product Backlog

| ID | Epic | User Story | MoSCoW | Priority | Points |
| --- | --- | --- | --- | --- | --- |
| US-001 | Auth | As a new user, I want to register with email & password, so that I can create an account and start shopping. | Must-Have | Critical | 8 |
| US-002 | Auth | As a registered user, I want to log in securely using JWT, so that my session is protected and persistent. | Must-Have | Critical | 5 |
| US-003 | Auth | As a logged-in user, I want to log out, so that I can end my session securely. | Must-Have | Critical | 2 |
| US-004 | Auth | As a user, I want to view and edit my profile (name, address, phone), so that my personal info is up to date. | Should-Have | High | 5 |
| US-005 | Auth | As a user, I want to reset my password via email link, so that I can recover my account if I forget my password. | Should-Have | Medium | 5 |
| US-006 | Auth | As a user, I want to log in via Google OAuth, so that I can sign in faster without a separate password. | Could-Have | Low | 8 |
| US-007 | Catalog | As an Admin, I want to add a new product (name, description, price, images, stock), so that customers can find and buy it. | Must-Have | Critical | 8 |
| US-008 | Catalog | As an Admin, I want to edit an existing product, so that I can keep product info accurate. | Must-Have | Critical | 5 |
| US-009 | Catalog | As an Admin, I want to delete a product, so that discontinued items are removed from the store. | Must-Have | High | 3 |
| US-010 | Catalog | As a Customer, I want to browse all products in a paginated catalog, so that I can discover items without scrolling endlessly. | Must-Have | Critical | 5 |
| US-011 | Catalog | As a Customer, I want to search products by keyword, so that I can quickly find what I am looking for. | Must-Have | Critical | 5 |
| US-012 | Catalog | As a Customer, I want to filter products by category and price range, so that I can narrow down my choices. | Must-Have | High | 5 |
| US-013 | Catalog | As a Customer, I want to view a product detail page with images, description, and reviews, so that I can make an informed purchase decision. | Must-Have | Critical | 5 |
| US-014 | Catalog | As a Customer, I want to see a "Related Products" section on the detail page, so that I can discover similar items. | Should-Have | Medium | 3 |
| US-015 | Catalog | As a Customer, I want to add a product to my Wishlist, so that I can save it for later consideration. | Could-Have | Low | 5 |
| US-016 | Cart | As a Customer, I want to add products to my cart, so that I can collect items before purchasing. | Must-Have | Critical | 5 |
| US-017 | Cart | As a Customer, I want to update item quantities in my cart, so that I can buy the right amount. | Must-Have | Critical | 3 |
| US-018 | Cart | As a Customer, I want to remove items from my cart, so that I can change my mind before checkout. | Must-Have | Critical | 2 |
| US-019 | Cart | As a Customer, I want to see the cart total (subtotal, taxes, shipping), so that I know the exact cost before paying. | Must-Have | High | 3 |
| US-020 | Cart | As a Customer, I want my cart to persist across sessions, so that I do not lose items when I close the browser. | Should-Have | High | 5 |
| US-021 | Cart | As a Customer, I want to apply a discount coupon code at checkout, so that I can benefit from promotional offers. | Could-Have | Medium | 8 |
| US-022 | Checkout | As a Customer, I want to enter a shipping address at checkout, so that my order is delivered to the correct location. | Must-Have | Critical | 3 |
| US-023 | Checkout | As a Customer, I want to pay securely via Stripe or Paymob, so that my transaction is processed safely. | Must-Have | Critical | 13 |
| US-024 | Checkout | As a Customer, I want to receive an order confirmation email after purchase, so that I have proof of my order. | Must-Have | High | 5 |
| US-025 | Checkout | As a Customer, I want to select a shipping method (standard / express), so that I can choose delivery speed vs. cost. | Should-Have | Medium | 3 |
| US-026 | Checkout | As a Customer, I want to save my card details for future payments, so that checkout is faster next time. | Could-Have | Low | 5 |
| US-027 | Orders | As a Customer, I want to view my order history with statuses, so that I can track all my purchases. | Must-Have | High | 5 |
| US-028 | Orders | As a Customer, I want to view full order details (items, costs, address), so that I have a clear record. | Must-Have | High | 3 |
| US-029 | Orders | As an Admin, I want to view all customer orders in a dashboard, so that I can manage fulfillment. | Must-Have | Critical | 5 |
| US-030 | Orders | As an Admin, I want to update order status (Pending → Processing → Shipped → Delivered), so that customers are kept informed. | Must-Have | Critical | 5 |
| US-031 | Orders | As a Customer, I want to cancel an order (while still Pending), so that I can change my mind before shipment. | Should-Have | Medium | 5 |
| US-032 | Orders | As a Customer, I want to request a return/refund, so that I can get my money back for faulty items. | Could-Have | Low | 8 |
| US-033 | Admin | As an Admin, I want a dashboard with KPI widgets (revenue, orders, new users), so that I have a real-time business overview. | Should-Have | High | 8 |
| US-034 | Admin | As an Admin, I want to manage user accounts (view, deactivate), so that I can handle account issues. | Should-Have | Medium | 5 |
| US-035 | Admin | As an Admin, I want to export order reports as CSV, so that I can analyze data in external tools. | Could-Have | Low | 5 |
| US-036 | Reviews | As a Customer, I want to leave a star rating and review on a product I purchased, so that other shoppers benefit from my experience. | Should-Have | Medium | 5 |
| US-037 | Reviews | As an Admin, I want to moderate and delete inappropriate reviews, so that the platform remains trustworthy. | Should-Have | Low | 3 |
| US-038 | Notif. | As a Customer, I want to receive an email when my order status changes, so that I stay informed without logging in. | Should-Have | Medium | 5 |
| US-039 | Notif. | As an Admin, I want to receive a notification when stock falls below a threshold, so that I can restock in time. | Could-Have | Low | 5 |

# SECTION 3 — MoSCoW PRIORITISATION

## 3.1  Prioritisation Summary

| Priority Tier | Description | # Stories | Story Points | Examples |
| --- | --- | --- | --- | --- |
| Must-Have | MVP Core | 22 | ~105 | Auth, Cart, Payment, Orders |
| Should-Have | Quality Add-ons | 11 | ~52 | Dashboard, Reviews, Emails |
| Could-Have | Nice to Have | 6 | ~34 | OAuth, Wishlist, Coupons |
| Won't Have (v1) | Future Scope | - | - | Mobile App, Multi-vendor |

## 3.2  Won't Have (v1.0 Scope Exclusions)

The following items are explicitly out of scope for this release. They are documented here to manage stakeholder expectations and may be revisited in a future product roadmap.

- Native Mobile Application (iOS / Android)

- Multi-vendor / Marketplace functionality

- Advanced analytics with BI dashboards

- Live chat / chatbot support

- Multi-language & currency support (internationalisation)

- Subscription / recurring payment plans

## 3.3  Prioritisation Rationale

Must-Have items form the irreducible core of a functional e-commerce platform. Without authentication, a product catalog, a working cart, and a payment gateway, the product has no value to any user.

Should-Have items significantly improve the user experience and admin efficiency. While the MVP works without them, they are planned for Sprint 3–4 as velocity allows.

Could-Have items are desirable enhancements (coupons, wishlist, OAuth) that require more effort with lower immediate business impact. They are deferred to Sprint 5 or a v1.1 release.

# SECTION 4 — SPRINT 0 & SPRINT 1 PLANS

## 4.1  Sprint 0 — Initialisation & Setup

| Sprint | Duration | Goal | DoD |
| --- | --- | --- | --- |
| Sprint 0 | 2 Weeks | All repos, pipelines, and schemas ready to code | Dev env set up on all machines; CI passing; ERD reviewed |

### Sprint 0 Task Breakdown

| Task ID | Category | Task Description | Owner | Estimate |
| --- | --- | --- | --- | --- |
| SP0-01 | Project Setup | Initialize Angular workspace with routing, lazy loading, and standalone components | Dev | 4h |
| SP0-02 | Project Setup | Scaffold Node.js + Express backend with folder structure (routes/controllers/services/models) | Dev | 3h |
| SP0-03 | Project Setup | Configure MongoDB Atlas cluster & Mongoose connection with .env management | Dev | 2h |
| SP0-04 | Project Setup | Set up Git repository, branching strategy (main/develop/feature/*), and PR templates | DevOps | 2h |
| SP0-05 | CI/CD | Configure GitHub Actions pipeline: lint → test → build on PR | DevOps | 4h |
| SP0-06 | Design | Finalise UI design system: color palette, typography, component library (Angular Material) | Design | 4h |
| SP0-07 | Architecture | Define API contract: RESTful endpoints, naming conventions, error response schema | Lead | 3h |
| SP0-08 | Architecture | Create Swagger/OpenAPI base file and integrate swagger-ui-express middleware | Dev | 3h |
| SP0-09 | Data Model | Design & document MongoDB schemas: User, Product, Category, Cart, Order, Review | Dev | 4h |
| SP0-10 | Planning | Create Jira/Trello board, import backlog, assign story points, and agree on Definition of Done | PO | 2h |
| SP0-11 | Environment | Set up .env templates for dev/staging/prod, configure ESLint + Prettier for both repos | Dev | 2h |
| SP0-12 | Security | Research & document JWT strategy, CORS policy, Helmet.js setup, and rate-limiting plan | Lead | 3h |

## 4.2  Sprint 1 — Authentication, Product Catalog & Cart Core

| Sprint | Duration | Goal | Velocity | Stories Covered | Points |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | 2 Weeks | Users can register, log in, browse products, and add items to cart | ~64 pts | US-001–003, US-007–013, US-016–019 | ~64 |

### Sprint 1 Task Breakdown

| Task ID | Category | Task Description | Stories | Owner | Points | Estimate |
| --- | --- | --- | --- | --- | --- | --- |
| SP1-01 | Auth | Build User model (schema + validation) and Auth service (register/login) | US-001,002 | Backend | 8 | 5h |
| SP1-02 | Auth | Implement JWT issuance, refresh-token strategy, and Auth middleware | US-002,003 | Backend | 5 | 3h |
| SP1-03 | Auth | Create role-based access guard (isAdmin / isCustomer) and attach to routes | US-002,003 | Backend | 3 | 2h |
| SP1-04 | Auth | Build Angular Auth module: register & login forms with reactive validation | US-001,002 | Frontend | 8 | 2h |
| SP1-05 | Auth | Implement AuthGuard & RoleGuard, intercept JWT in HTTP requests | US-002,003 | Frontend | 5 | 4h |
| SP1-06 | Catalog | Implement Product & Category Mongoose models with indexes | US-007,008 | Backend | 5 | 4h |
| SP1-07 | Catalog | Build CRUD product API endpoints with image upload (Multer + Cloudinary) | US-007-009 | Backend | 8 | 3h |
| SP1-08 | Catalog | Add product search (text index), filter (category/price), and pagination | US-010-012 | Backend | 8 | 3h |
| SP1-09 | Catalog | Build product catalog page with Angular grid, search bar, filter sidebar | US-010-012 | Frontend | 8 | 4h |
| SP1-10 | Catalog | Build product detail page with image gallery, description, and Add-to-Cart CTA | US-013 | Frontend | 5 | 2h |
| SP1-11 | Cart | Implement Cart model & API (add/update/remove/get by userId) | US-016-019 | Backend | 5 | 2h |
| SP1-12 | Cart | Build cart drawer/page in Angular with live quantity controls and total calculation | US-016-019 | Frontend | 8 | 3h |
| SP1-13 | Testing | Write unit tests for Auth service (register, login, token validation) — Jest | US-001,002 | Backend | 3 | 5h |
| SP1-14 | Testing | Write unit tests for Product service (CRUD, search, filter) — Jest | US-007-012 | Backend | 3 | 6h |
| SP1-15 | Docs | Update Swagger docs for all Auth, Product, and Cart endpoints | All | Lead | 2 | 4h |

## 4.3  Scrum Ceremonies Schedule

| Ceremony | Frequency | Duration | Purpose |
| --- | --- | --- | --- |
| Sprint Planning | Start of Sprint | 2 hours | Decompose stories into tasks; agree on sprint goal and capacity |
| Daily Stand-up | Every weekday | 15 mins | What did I do? What will I do? Any blockers? |
| Sprint Review | End of Sprint | 1 hour | Demo working software to Product Owner; collect feedback |
| Sprint Retrospective | End of Sprint | 45 mins | What went well / could improve / action items for next sprint |
| Backlog Refinement | Mid-Sprint | 1 hour | Estimate, split, and clarify upcoming stories |

## 4.4  Definition of Done (DoD)

| Category | Done Criterion |
| --- | --- |
| Code | Feature branch merged to develop via approved Pull Request |
| Code | No linting errors (ESLint) or TypeScript compilation warnings |
| Testing | Unit tests written and passing (coverage ≥ 60% for new code) |
| Testing | Manual QA performed in a local or staging environment |
| API | Swagger documentation updated for any new/modified endpoints |
| Review | Peer code review completed by at least one other developer |
| Acceptance | Product Owner has accepted the story against acceptance criteria |
| Deploy | Feature tested in staging environment without regression failures |

# SECTION 5 — RELEASE ROADMAP & VELOCITY

## 5.1  Sprint Timeline Overview

| Sprint | Duration | Theme | Stories / Tasks | Story Points |
| --- | --- | --- | --- | --- |
| Sprint 0 | 2 weeks | Initialization | Repos, CI/CD, DB, schema, design system, API contract | — |
| Sprint 1 | 2 weeks | Auth + Catalog + Cart Core | US-001–003, US-007–013, US-016–019 | ~64 |
| Sprint 2 | 2 weeks | Checkout + Payment | US-022–024, US-027–030 | ~34 |
| Sprint 3 | 2 weeks | Admin Dashboard + Orders | US-029–031, US-033–034 | ~26 |
| Sprint 4 | 2 weeks | Should-Have Polishing | US-004,005,014,020,025,036–038 | ~34 |
| Sprint 5 | 2 weeks | Could-Have + Bug-Fix | US-006,015,021,032,035,039 | ~28 |
| Sprint 6 | 1 week | Hardening & Launch | Performance, security audit, final docs, cloud deploy | — |

## 5.2  Risk Register

| # | Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R-01 | Payment gateway integration delays | Medium | High | Spike in Sprint 1; use Stripe test keys early; fallback to mock payment service for demo |
| R-02 | Scope creep from adding non-MVP features | High | High | Strict MoSCoW adherence; PO must approve any story promotions |
| R-03 | Team member unavailability | Medium | Medium | Cross-functional pairing; document all setup steps; no knowledge silos |
| R-04 | MongoDB performance bottlenecks | Low | Medium | Add indexes at schema design; monitor with Atlas performance advisor |
| R-05 | JWT security vulnerability | Low | High | Short token expiry + refresh tokens; use Helmet.js; regular dependency audit |

## 5.3  Technology Architecture Summary

| Layer | Technology | Key Libraries / Tools |
| --- | --- | --- |
| Frontend | Angular 21+ | Angular Material, RxJS, NgRx (state), Angular Router, Reactive Forms |
| Backend | Node.js + Express | Mongoose, JWT (jsonwebtoken), bcryptjs, Multer, Nodemailer, Helmet, cors, express-rate-limit |
| Database | MongoDB Atlas | Mongoose ODM, text indexes, aggregation pipeline |
| Auth | JWT + bcryptjs | Access token (15m) + Refresh token (7d) strategy |
| Storage | Cloudinary | Product image upload via Multer middleware |
| Payments | Stripe / Paymob | Client-side Elements + server-side intent creation |
| CI/CD | GitHub Actions | Lint → Test → Build pipeline on every PR to develop |
| Hosting | Vercel + Railway | Angular SPA on Vercel; Express API on Railway / Render |
| Docs | Swagger / OpenAPI | swagger-ui-express + swagger-jsdoc |
| Testing | Jest + Supertest | Unit tests (services), integration tests (API routes) |

Document prepared for academic graduation project submission.  All stories and tasks are Jira/Trello-ready.